## Fit Gap Analysis
Expertise Company – T&L Implementation: Fit-Gap Analysis Matrix
Fit Status Legend: ✅ Fully Available ¦ ⚠ Partially Available ¦ ❌ Not Available
# | RFP Section / Requirement Reference | Phase | Requirement Description | Fit Status | Solution Description (How the requirement is addressed) | Reference Evidence (Document / Screen / Demo Ref) | Gap Description (If Applicable) | Proposed Approach to Address Gap | Suggested Timeline
PROJECT GOVERNANCE & KICK-OFF
1 | Section 2.4 / PG-01 | Inception | Project charter & communication plan | ✅ Fully Available | Our solution delivery methodology includes a standard project charter template, RACI matrix, and structured communication plan prepared at project inception. | Implementation Methodology Document | – | – | Wk 1–2
2 | Section 2.4 / PG-02 | Inception | Roles & responsibilities matrix (RACI) | ✅ Fully Available | A RACI matrix covering all project workstreams — functional, integration, technical, and testing — is prepared and agreed during the inception phase. | Project Governance Template | – | – | Wk 1–2
3 | Section 2.4 / PG-03 | Inception | Risk register & mitigation plan | ✅ Fully Available | Risk register maintained throughout the project with proactive identification, classification, impact assessment, and mitigation actions reviewed weekly. | Risk Register Template | – | – | Wk 2–3
4 | Section 2.4 / PG-04 | Inception | Governance framework & escalation matrix | ✅ Fully Available | Governance framework defines steering committee, project sponsor, workstream leads, and escalation paths with defined SLA for issue resolution. | Governance Framework Document | – | – | Wk 2
5 | Section 2.4 / PG-05 | Inception | Detailed project plan with milestones | ✅ Fully Available | Full project plan covering all phases — Inception, Design, Build, Integration, UAT, Go-Live, and Hypercare — with milestone-based delivery tracked in project management tool. | Project Plan / MS Project / Jira | – | – | Wk 2–3
MASTER DATA MANAGEMENT
6 | Section 3.8.2-A / MDM-01 | Design | Location & geo master (sites, depots, pickup/drop, geo-fence) | ✅ Fully Available | Application supports full location master setup including project sites, depots, pickup/drop points, and geo-fence polygon definitions linked to GPS coordinates. | Application Master Data Module – Demo Screen MDM-01 | – | – | Wk 5–7
7 | Section 3.8.2-B / MDM-02 | Design | Route master (ID, origin, destination, stops, distance) | ✅ Fully Available | Route master configuration supports route ID, origin/destination, intermediate stops, distance, estimated time, and compliance flags. | Application Route Master Config Screen | – | – | Wk 5–7
8 | Section 3.8.2-C / MDM-03 | Design | Compliance & document master (types, authority, validity, alerts) | Partially Availabl | Document master supports all document types (Registration, Insurance, Permit, License), issuing authority, validity period, alert thresholds, and KSA regulatory categories. | Document repository is available - Demo | – | – | Wk 5–7
9 | Section 3.8.5-B / MDM-04 | Design | Light vehicle master & employee eligibility master | ✅ Fully Available | Light vehicle master includes vehicle class, model level (M1/M2/M3), eligibility grade mapping, ownership type, GPS tag, and status. Employee eligibility master links grade to vehicle type with approval authority. | Light Vehicle Master – Application Config | – | – | Wk 6–8
10 | Section 3.8.3-A,B,C / MDM-05 | Design | Bus master, driver & passenger/employee mapping master | ✅ Fully Available | Bus master includes Bus ID (linked to SAP Equipment No.), seating capacity, GPS device ID, ownership. Driver master includes license category, shift eligibility. Passenger mapping links employees to routes and pickup points. | Bus Management Master Data Screens | – | – | Wk 6–8
11 | Section 3.8.4-A / MDM-06 | Design | Heavy vehicle / equipment & permit master | ✅ Fully Available | Equipment master covers trucks, trailers, low-beds, cranes with load capacity, axle details, compliance profile (MIZAN, TAMM), GPS tag, and vendor association. Permit master covers permit type, valid routes, and load restrictions. | Heavy Vehicle Master Data Module | – | – | Wk 6–8
12 | Section 3.8.6 / MDM-07 | Design | Maintenance & condition master (SAP PM aligned) | Partially Available | Maintenance master supports maintenance category, breakdown type, service schedule, and vehicle condition codes. Need to be Aligned with SAP PM for bi-directional status synchronization. | Maintenance Master | – | – | Wk 6–8
13 | Section 3.8.7 / MDM-08 | Build | Data quality controls — duplicate prevention, field validation, reconciliation | ✅ Fully Available | Platform enforces mandatory field validation, duplicate prevention rules, periodic master data reconciliation with SAP, | Data Quality Controls Config – Application Admin | – | – | Wk 9–11
LIGHT VEHICLE MANAGEMENT
14 | Section 3.4.1 / LV-01 | Design | AS-IS process documentation | ✅ Fully Available | Business analyst workshops conducted to document current state processes for all light vehicle operations including allocation, return, and compliance tracking. | Business Blueprint Document – Phase 1 Design | – | – | Wk 3–5
15 | Section 3.4.1 / LV-02 | Design | TO-BE process / business blueprint | ✅ Fully Available | TO-BE process design maps all optimized workflows for light vehicle request, approval, allocation, return, and compliance aligned with T&L platform capabilities. | Business Blueprint – TO-BE Process Design | – | – | Wk 4–6
16 | Section 3.4.1 / LV-03 | Build | Vehicle request config (permanent, temporary, one-time/trip-based) | ✅ Fully Available | Application supports three vehicle request types: permanent allocation, temporary allocation, and one-time/trip-based requests — each with distinct approval paths and policy controls. | Vehicle Request Module – Demo / Config Screens | – | – | Wk 7–10
17 | Section 3.4.1 / LV-04 | Build | Vehicle request approval workflow | ✅ Fully Available | Approval workflows configured per request type, role, grade, and policy. Supports parallel/sequential approvals, SLA tracking, and delegation. | Workflow Builder – Light Vehicle Approval Config | – | – | Wk 7–10
18 | Section 3.4.1 / LV-05 | Build | Vehicle allocation | ✅ Fully Available | Manual and system-assisted vehicle allocation based on request type, availability, and policy. Allocation linked to cost center and department. | Vehicle Allocation Module – Application Demo | – | – | Wk 7–10
19 | Section 3.4.1 / LV-06 | Build | Smart / intelligent auto-allocation | ⚠ Partially Available | Recommendation engine available. Auto-allocation logic can suggest vehicles based on availability, location, and utilization history. Full AI-driven auto-assignment requires configuration and tuning to client-specific rules. | Intelligent Allocation Module – Demo | Full autonomous auto-allocation requires rule configuration and testing for grade eligibility, owned vs. leased preference, and shift-based demand. | Configure recommendation engine rules; build preference logic for owned-first allocation; test and validate with Expertise data. | Wk 16–19
20 | Section 3.4.1 / LV-07 | Build | Vehicle pool & grade eligibility setup (M1/M2/M3) | ✅ Fully Available | Vehicle pool module supports grade-based eligibility (M1, M2, M3) mapped to vehicle categories (SUV, Sedan, Small SUV) with HR exception approval workflow. | Vehicle Pool Config – Grade Eligibility Mapping | – | – | Wk 7–10
21 | Section 3.4.1 / LV-08 | Build | Owned vs leased vehicle segregation logic | ✅ Fully Available | Platform maintains clear ownership type flags (Owned / Vendor-Leased) on all vehicles. Allocation logic prioritizes owned fleet. Reports and dashboards display segregated views. | Vehicle Master – Ownership Config; Fleet Dashboard | – | – | Wk 8–10
22 | Section 3.4.1 / LV-09 | Build | Intelligent allocation & recommendation engine config | ⚠ Partially Available | Recommendation engine considers vehicle availability, current location, utilization history, and upcoming demand. Configuration required to tune client-specific allocation preferences. | Recommendation Engine Config Module | Engine parameters need tuning for Expertise-specific rules including grade restrictions, project-location preferences, and owned-vehicle priority. | Configure and calibrate recommendation engine parameters with Expertise operational data; validate outputs with transport admin. | Wk 9–12
23 | Section 3.4.1 / LV-10 | Build | Breakdown & maintenance alert workflows | ✅ Fully Available | Breakdown reporting triggers automatic alerts to maintenance teams. Notification workflows configurable via workflow builder. Repair checklist and maintenance history tracked per vehicle. | Breakdown Alert Workflow – Application Demo | – | – | Wk 10–12
24 | Section 3.4.1 / LV-11 | Build | Document & compliance management (Insurance, Istimara) | ✅ Fully Available | All vehicle documents (Insurance, Istimara, ownership records, transfer history) managed centrally with expiry alerts, compliance dashboards, and audit trail. | Document Management Module – Application Demo | – | – | Wk 10–12
25 | Section 3.4.1 / LV-12 | Integration | Financial cross-charge & vendor invoicing integration (SAP MM/CO) | ⚠ Partially Available | Integration framework supports financial postings and cross-charge to requesting department/cost center. SAP MM/CO integration for vendor invoicing requires configuration of SAP CPI/PI-PO middleware. | Integration Architecture Document | SAP MM/CO integration requires API mapping, SAP CPI configuration, and testing with Expertise SAP environment. | Design integration specs; configure SAP CPI adapters; conduct integration testing with Expertise SAP S/4HANA system. | Wk 13–16
26 | Section 3.4.1 / LV-13 | Build | Ownership tracking — ownership transfer records | ✅ Fully Available | Vehicle master maintains full ownership history including current and previous owners, transfer records, and handover dates with complete audit trail. | Vehicle Ownership History – Application Screen | – | – | Wk 7–10
27 | Section 3.4.1 / LV-14 | Build | HR exception approval workflow for grade eligibility overrides | ✅ Fully Available | Exception workflow supports HR approval for grade eligibility overrides with justification capture, multi-level approval, and policy documentation. | Exception Workflow Config – Application Demo | – | – | Wk 7–10
28 |  | Build | Chain of ownership changes, Cost tracking, accident tracking, damages tracking, fuel tracking by users and tracking by assets, maintainance cost with recommendation model to sell or keep | Not Available
BUS MANAGEMENT (EMPLOYEE TRANSPORTATION)
28 | Section 3.4.2 / BM-01 | Build | Bus master data & seating capacity setup | ✅ Fully Available | Bus master includes Bus ID (SAP Equipment No. linked), make/model, seating capacity, plate number, ownership type, GPS device ID, vendor reference, and operational status. | Bus Master Data Config – Application Demo | – | – | Wk 7–9
29 | Section 3.4.2 / BM-02 | Build | Route planning & pickup/drop point configuration | ✅ Fully Available | Route planning module supports full route definition with pickup/drop points, distance, estimated time, shift-based assignment, and period-based allocation (weekly/monthly). | Route Planning Module – Application Demo | – | – | Wk 8–11
30 | Section 3.4.2 / BM-03 | Build | Shift-based daily trip planning automation | ⚠ Partially Available | Shift-based trip planning framework is available. Full automation of daily trip plans based on SAP roster and leave data requires development of automated scheduling engine. | Trip Planning Module – Partial Demo | Automated daily schedule generation based on real-time SAP roster/leave data requires development of scheduling automation logic. | Develop automated trip scheduling engine integrated with SAP roster feed; configure shift-to-route mapping; validate with Expertise shift patterns. | Wk 9–12
31 | Section 3.4.2 / BM-04 | Integration | SAP roster & leave integration (auto-exclusion from schedules) | ⚠ Partially Available | Integration framework supports SAP HCM/SuccessFactors connectivity. Auto-exclusion of employees on leave from pickup/drop schedules and dynamic route adjustment requires integration development. | Integration Architecture – SAP Roster | SAP roster and leave integration API mapping, real-time sync, and auto-exclusion logic requires integration development and testing. | Develop SAP CPI integration for roster/leave feed; implement auto-exclusion rule engine; validate with Expertise SAP environment. | Wk 13–15
32 | Section 3.4.2 / BM-05 | Build | Intelligent route optimisation & consolidation | ⚠ Partially Available | Route optimization capability identifies low-occupancy routes and provides consolidation recommendations based on origin/destination, shift timing, planned occupancy, and route distance. | Route Optimization Module – Partial Demo | Full route optimization engine requires configuration of consolidation thresholds and validation with Expertise route data. | Configure consolidation rules and occupancy thresholds; implement route consolidation recommendation engine; validate outputs. | Wk 16–19
33 | Section 3.4.2 / BM-06 | Build | Geo-fence violation alerts & off-day operation controls | ⚠ Partially Available | Geo-fence alert framework is available. Integration with GPS (Saudi Ex) required for real-time violation detection. Off-day operation control alerts require GPS integration. | Geo-fence Module; GPS Integration Spec | Requires GPS (Saudi Ex) integration for real-time geo-fence violation detection and alert triggering. | Integrate Saudi Ex GPS feed; configure geo-fence zones; implement violation alert rules and notification workflows. | Wk 11–13
34 | Section 3.4.2 / BM-07 | Build | Bus compliance document management (MIZAN, Istimara, Insurance) | Not Available | Document management framework supports insurance and Istimara. MIZAN-specific permit type and KSA regulatory compliance category requires additional configuration and development. | Document Management Module | MIZAN permit type configuration and KSA-specific regulatory category requires development for bus compliance. | Develop MIZAN document type and compliance category; integrate expiry alerts and compliance dashboard for bus fleet. | Wk 10–12
35 | Section 3.4.2 / BM-08 | Integration | Financial cross-charge to departments/projects via SAP | Not Available | Financial cross-charge framework available within the platform. SAP CO/PS integration for automated posting to cost centers and projects requires SAP CPI configuration. | Financial Integration Spec | SAP CO/PS integration for cross-charge posting requires API design, SAP CPI configuration, and testing. | Design and configure SAP CO/PS integration via SAP CPI; test cross-charge postings with Expertise SAP environment. | Wk 13–16
28 |  | Build | Chain of ownership changes, Cost tracking, accident tracking, damages tracking, fuel tracking by users and tracking by assets, maintainance cost with recommendation model to sell or keep | Not Available
36 | Section 3.4.2 / BM-09 | Build | Period-based bus allocation (weekly/monthly planning) | ✅ Fully Available | Bus allocation module supports period-based planning (weekly, monthly) with capacity tracking, route assignment, and scheduled occupancy visibility. | Bus Period Allocation Config – Application Demo | – | – | Wk 10–13
HEAVY VEHICLE & EQUIPMENT MANAGEMENT
37 | Section 3.4.3 / HV-01 | Build | Equipment master data setup (trucks, trailers, low-beds, cranes) | ✅ Fully Available | Equipment master covers all heavy vehicle categories (trucks, trailers, low-beds, cranes, heavy equipment) with full attributes including load capacity, axle details, compliance profile, and ownership. | Equipment Master Data Module – Application Demo | – | – | Wk 7–9
38 | Section 3.4.3 / HV-02 | Build | Transport request & approval workflow (35–40+ daily requests) | ✅ Fully Available | Transport request module handles high-volume daily requests with configurable approval workflows, priority handling, and automated routing based on vehicle type and request attributes. | Heavy Vehicle Request Module – Demo | – | – | Wk 8–11
39 | Section 3.4.3 / HV-03 | Build | Transport vehicle request approval workflow | ✅ Fully Available | Multi-level approval workflow for heavy vehicle requests with configurable approval steps, parallel/sequential routing, and SLA-based escalation. | Workflow Builder – Heavy Vehicle Approval Config | – | – | Wk 8–11
40 | Section 3.4.3 / HV-04 | Build | Transport vehicle auto-allocation / suggestion | ✅ Fully Available | System provides vehicle suggestion based on load requirements, route constraints, permit requirements, current availability, and compliance readiness. | Vehicle Suggestion Engine – Application Demo | – | – | Wk 8–11
41 | Section 3.4.3 / HV-05 | Build | Automatic data population based on requestor's mobilization and department | ✅ Fully Available | Request form auto-populates employee details (department, cost center, project/WBS, location) from SAP Employee Master integration upon requester identification. | Auto-Population Config – Request Form Demo | – | – | Wk 8–11
42 | Section 3.4.3 / HV-06 | Build | Auto form filling | ✅ Fully Available | Smart form auto-fills requester details, department, cost center, project code, and location fields based on SAP employee data reducing manual entry and errors. | Smart Form Config – Application Demo | – | – | Wk 8–11
43 | Section 3.4.3 / HV-07 | Build | Intelligent vehicle recommendation engine (load, route, availability) | ✅ Fully Available | Recommendation engine evaluates vehicle suitability based on load weight, dimensions, route constraints, permit requirements, current availability, and real-time GPS location. | Recommendation Engine – Heavy Vehicle Demo | – | – | Wk 10–13
44 | Section 3.4.3 / HV-08 | Build | KSA regulatory compliance setup (MIZAN, TAMM, MVPI, Tasriya, Naql) | Not Available | Compliance profile framework is available on the equipment master. KSA-specific regulatory categories (MIZAN, TAMM, MVPI, Tasriya, Naql) require development of compliance rule sets and permit validation workflows. | Equipment Master – Compliance Profile | KSA regulatory compliance categories and permit validation workflows require specific development for MIZAN, TAMM, MVPI, Tasriya, and Naql requirements. | Design and develop KSA compliance rule set for each regulatory category; build permit validation engine; integrate with regulatory alert workflows. | Wk 10–13
45 | Section 3.4.3 / HV-09 | Build | Permit validation prior to dispatch | ✅ Fully Available | System validates all required permits against equipment compliance profile before allowing dispatch confirmation. Invalid or expired permits trigger blocking alerts. | Permit Validation – Pre-Dispatch Check Demo | – | – | Wk 11–13
46 | Section 3.4.3 / HV-10 | Build | Vendor RFQ creation, bid comparison & assignment workflow | ⚠ Partially Available | RFQ framework supports vendor invitation and bid collection. Full bid comparison matrix and vendor selection workflow require development. | Vendor RFQ Module – Partial Demo | Structured bid comparison matrix and automated vendor scoring/selection workflow require development. | Develop bid comparison module and vendor selection workflow; integrate with vendor master and rate card master. | Wk 9–12
47 | Section 3.4.3 / HV-11 | Integration | Trip execution monitoring & GPS-based tracking | Not Available | Trip execution milestone tracking available within the platform. Real-time GPS tracking requires integration with Saudi Ex GPS system. | Trip Monitoring Module; GPS Integration Spec | GPS-based real-time trip tracking requires Saudi Ex integration development. | Develop Saudi Ex GPS integration; configure real-time trip status update; implement geo-visibility on live map. | Wk 13–16
48 | Section 3.4.3 / HV-12 | Build | Proof of delivery (driver/vendor upload) & trip completion | ✅ Fully Available | Proof of delivery supports document/photo upload by driver or vendor. Trip completion confirmation triggers workflow and SAP cost posting. | Driver photo clicking demo shown | – | – | Wk 11–13
49 | Section 3.4.3 / HV-13 | Integration | SAP PS/CO integration for project-based costing | Not Available | Integration framework available. SAP PS/CO integration for project-based cost allocation requires SAP CPI configuration, WBS mapping, and end-to-end testing. | SAP Integration Architecture | SAP PS/CO integration requires API design, SAP CPI configuration, WBS/project mapping, and testing with Expertise SAP environment. | Design SAP PS/CO integration specs; configure SAP CPI; test project-based cost posting with Expertise system. | Wk 14–17
28 |  | Build | Chain of ownership changes, Cost tracking, accident tracking, damages tracking, fuel tracking by users and tracking by assets, maintainance cost with recommendation model to sell or keep | Not Available
50 | Section 3.4.3 / HV-14 | Build | Equipment availability forecasting (release & next availability) | ✅ Fully Available | Equipment availability module tracks current assignments, planned maintenance, and estimated release dates providing next availability forecasting for planning. | Equipment Availability Dashboard – Demo | – | – | Wk 16–19
DRIVER MANAGEMENT
51 | Section 3.4.4 / DM-01 | Build | Centralised driver master data (owned & vendor drivers) | ✅ Fully Available | Single driver master covers owned and vendor drivers with full profile including Employee ID (SAP), license category, Iqama, insurance, and current/historical assignment. | Driver Master Module – Application Demo | – | – | Wk 7–9
52 | Section 3.4.4 / DM-02 | Build | Document management (license, Iqama, insurance) & expiry alerts | ✅ Fully Available | Driver document management covers driving license (issue/expiry), Iqama, and insurance with automated expiry alerts, compliance dashboards, and audit trail. | Driver Document Management – Demo | – | – | Wk 8–11
53 | Section 3.4.4 / DM-03 | Build | Driver utilisation & availability tracking (trips, idle time, absenteeism) | Partially Available. | Driver utilization module tracks trips completed, idle vs active time, and absenteeism linked to SAP roster/leave data. | Driver Utilization Dashboard – Demo | SAP Integration Required | – | Wk 9–12
54 | Section 3.4.4 / DM-04 | Build | Driver communication | ✅ Fully Available | In-app messaging and notification system enables direct communication with drivers for trip assignments, schedule changes, alerts, and emergency notifications. | Driver Communication Module – Demo | – | – | Wk 9–12
55 | Section 3.4.4 / DM-05 | Build | Driver dashboard | ✅ Fully Available | Role-based driver dashboard displays today's assignments, trip status, document expiry alerts, and performance KPIs accessible via mobile-friendly interface. | Driver Dashboard – Mobile Demo | – | – | Wk 9–12
56 | Section 3.4.4 / DM-06 | Build | Driver trip logging | ✅ Fully Available | All driver trips logged with start/end time, route taken, distance, stops, deviations, and trip status. Linked to vehicle GPS data for audit trail. | Trip Logging Module – Application Demo | – | – | Wk 9–12
57 | Section 3.4.4 / DM-07 | Build | Performance & safety insights (violations, on-time rate, completion rate) | ✅ Fully Available | Driver performance analytics covers safety violations (from GPS), on-time pickup/drop %, route deviation count, trip completion rate, and incident frequency. | Driver Performance Analytics – Demo | – | – | Wk 10–13
58 | Section 3.4.4 / DM-08 | Integration | SAP Employee Master & roster integration | Not Available | Integration framework supports SAP HCM/SuccessFactors connectivity. Employee and driver master sync, roster, shift, and leave integration requires SAP CPI configuration. | SAP Integration Architecture | SAP Employee Master and roster integration requires API design, SAP CPI configuration, and testing. | Design SAP HCM/SuccessFactors integration specs; configure SAP CPI; validate driver/employee master sync with Expertise SAP. | Wk 13–15
VEHICLE VIOLATIONS & COMPLIANCE
59 | Section 3.4.5 / VC-01 | Build | Violation capture config (speeding, geo-fence breach, doc non-compliance) | Partially Available | Violation capture module configured for speeding, route deviation, geo-fence breach, and document non-compliance. Manual entry and GPS-triggered violations supported. | Violation Capture Config – Application Demo | – | – | Wk 9–12
60 | Section 3.4.5 / VC-02 | Integration | Multi-source violation ingestion (GPS, manual entry, govt portal) | Not Available | Manual entry and GPS-based violations supported. Government portal reference ingestion requires integration development. | Violation Ingestion Module | Government portal integration for automated violation ingestion requires API development. | Develop government portal integration or manual import workflow for government-issued violation references. | Wk 13–15
61 | Section 3.4.5 / VC-03 | Build | Violation lifecycle management (reported → under review → resolved) | ⚠ Partially Available | Violation status tracking partially available. Full lifecycle management including Disputed status and structured resolution workflow requires development. | Violation Module – Partial Demo | Disputed status handling and structured lifecycle workflow (Reported → Under Review → Disputed → Resolved/Closed) requires development. | Develop complete violation lifecycle workflow with all status transitions, approval steps, and audit trail. | Wk 10–12
62 | Section 3.4.5 / VC-04 | Build | Financial & disciplinary linkage (cost allocation, vendor penalties, driver record) | ⚠ Partially Available | Driver record linkage available. Financial cost allocation to department/project and vendor penalty processing require development and SAP integration. | Driver Records Module | Financial linkage for department cost allocation and vendor penalty processing requires development and SAP CO integration. | Develop financial linkage module for violation cost allocation; integrate vendor penalty workflow with SAP MM. | Wk 11–13
VENDOR & RFQ MANAGEMENT
63 | Section 3.5.4 / VR-01 | Integration | Vendor master data setup & SAP MM integration | ⚠ Partially Available | Vendor master data management available within the platform. SAP MM integration for vendor master sync requires SAP CPI configuration. | Vendor Master Module; SAP Integration Spec | SAP MM integration for vendor master synchronization requires API design and SAP CPI configuration. | Design SAP MM vendor master integration; configure SAP CPI adapter; test bi-directional sync. | Wk 12–15
64 | Section 3.4.3 / VR-02 | Build | RFQ creation, vendor invitation & bid comparison workflow | ⚠ Partially Available | RFQ creation and vendor invitation framework available. Structured bid comparison matrix and vendor scoring workflow require development. | RFQ Module – Partial Demo | Bid comparison matrix and automated vendor scoring/selection workflow require development. | Develop bid comparison and vendor selection modules; build approval workflow for vendor award. | Wk 9–12
65 | Section 3.8.4-D / VR-03 | Build | Rate card master (trip-based / KM-based pricing, validity period, previously quoted rate for similar trip) | ⚠ Partially Available | Rate card master supports trip-based and KM-based pricing models with validity periods, vendor-specific rates, and contract references. |  | Development | Will be developed based on user inputs | Wk 10–12
66 | Section 3.7.2.4 / VR-04 | Build | Vendor performance KPI tracking (SLA, cost variance, invoice accuracy) | ✅ Fully Available | Vendor performance dashboard tracks SLA compliance %, cost variance vs contract, service rejection/failure rate, compliance adherence, and invoice accuracy rate. | Vendor Performance Dashboard – Demo | – | – | Wk 12–15
SAP S/4HANA INTEGRATION
67 | Section 3.5.1 / SI-01 | Integration | Employee & driver master integration (HCM / SuccessFactors) | Not Available | Integration framework and API connectors available. SAP HCM/SuccessFactors employee and driver master sync requires SAP CPI configuration and testing with Expertise environment. | SAP Integration Architecture Document | Requires SAP CPI configuration, API mapping, and testing with Expertise SAP HCM/SuccessFactors. | Design integration specs; configure SAP CPI; develop field mapping; conduct integration testing. | Wk 11–14
68 | Section 3.5.2 / SI-02 | Integration | Employee roster, shift & leave integration | Not Available | Roster and leave integration framework available. Auto-exclusion logic and dynamic route adjustment require integration development and testing. | SAP Integration Architecture | Real-time roster/leave sync and auto-exclusion logic require SAP CPI integration development. | Develop SAP CPI integration for roster/leave; implement auto-exclusion engine; validate with Expertise data. | Wk 11–14
69 | Section 3.5.3 / SI-03 | Integration | Vehicle & equipment master sync (SAP PM / EAM) | Not Available | Equipment master integration framework supports SAP PM/EAM connectivity. Status synchronization (Active, Under Maintenance, Breakdown) requires bi-directional API configuration. | SAP Integration Architecture | SAP PM/EAM bi-directional sync requires API design, SAP CPI adapter configuration, and testing. | Design SAP PM integration specs; configure SAP CPI; test equipment master and status sync. | Wk 12–15
70 | Section 3.5.4 / SI-04 | Integration | Vendor & vendor-vehicle integration (SAP MM + PM) | Not Available | Vendor and vehicle-to-vendor association integration requires SAP MM + PM integration via SAP CPI for clear fleet segregation. | SAP Integration Architecture | SAP MM + PM integration for vendor-vehicle association requires SAP CPI configuration and testing. | Design SAP MM+PM integration; configure SAP CPI; test vendor master and equipment association sync. | Wk 12–15
71 | Section 3.5.5 / SI-05 | Integration | Maintenance & availability integration — block vehicle on maintenance (SAP PM) | Not Available | Maintenance blocking logic available in platform. SAP PM maintenance notification trigger and status synchronization requires integration development. | SAP Integration Architecture | SAP PM maintenance notification trigger and vehicle blocking logic requires integration development. | Develop SAP PM integration for maintenance notifications; implement vehicle blocking on maintenance status. | Wk 13–16
72 | Section 3.5.6 / SI-06 | Integration | Project, cost centre & financial integration (SAP PS / CO) | Not Available | Financial integration framework available. SAP PS/CO integration for WBS assignment, cost center allocation, and chargeback automation requires SAP CPI configuration. | SAP Integration Architecture | SAP PS/CO integration for project costing and chargeback requires SAP CPI configuration and testing. | Design SAP PS/CO integration; configure SAP CPI; test cost center and WBS posting with Expertise system. | Wk 13–17
73 | Section 3.5.7 / SI-07 | Integration | Automated cross-charge & vendor invoicing via SAP | Not Available | Cross-charge automation framework available. SAP MM/FI integration for automated vendor invoicing requires SAP CPI configuration and end-to-end testing. | SAP Integration Architecture | Automated vendor invoicing via SAP MM/FI requires integration design, SAP CPI configuration, and testing. | Design SAP MM/FI integration for vendor invoicing; configure SAP CPI; test end-to-end invoicing process. | Wk 14–17
74 | Section 3.5.7 / SI-08 | Integration | Alerts, events & notification integration (Fiori Inbox / email / SMS) | Not Available | In-app and email notifications available. SAP Fiori Inbox integration and SMS gateway configuration require additional setup. | Notification Module Config | SAP Fiori Inbox integration requires SAP CPI configuration. SMS gateway requires third-party SMS provider setup. | Configure SAP Fiori Inbox integration; set up SMS gateway; test multi-channel notification delivery. | Wk 14–16
75 | Section 3.5.8.2 / SI-09 | Integration | GPS (Saudi Ex) real-time integration | Not Available | GPS integration framework available with standard REST/API connectors. Saudi Ex GPS integration requires API specification from Saudi Ex and integration development. | GPS Integration Architecture | Saudi Ex GPS API specification required; real-time vehicle location, speed, idle time, and route adherence integration to be developed. | Obtain Saudi Ex API documentation; develop GPS integration; configure real-time data feed; test with live vehicles. | Wk 13–16
76 | Section 3.4.4 / SI-10 | Integration | ZKT Biotime attendance device integration | Not Available | Attendance data integration framework available. ZKT Biotime API/connector requires development for real-time attendance data sync to support driver availability tracking. | Integration Architecture | ZKT Biotime API integration for attendance data sync requires development. | Obtain ZKT Biotime API specs; develop integration connector; test attendance data sync. | Wk 13–15
77 | Section 3.4.1 / SI-11 | Integration | Petro APP fuel usage integration | Not Available | Fuel data integration framework available. Petro APP API integration requires specification from Expertise and connector development for fuel usage data sync per vehicle. | Integration Architecture | Petro APP API specification required for fuel usage data integration development. | Obtain Petro APP API documentation; develop integration; test fuel data sync per vehicle. | Wk 14–16
78 | Section 3.5.8.4 / SI-12 | Integration | KSA TGA / Naql / MIZAN regulatory data alignment | Not Available | Compliance data framework available. KSA regulatory authority integration (TGA, Naql, MIZAN) requires development of permit tracking, route validation, and regulatory alert workflows. | Compliance Module; Regulatory Integration Spec | KSA regulatory authority API access and integration for TGA, Naql, and MIZAN data alignment requires development. | Assess API availability from TGA/Naql/MIZAN; develop integration or structured data alignment workflows; implement permit and route validation. | Wk 14–17
79 | Section 3.10 / SI-13 | Integration | API integration layer (SAP CPI / PI-PO) config & error monitoring | Not Available | API-based integration architecture designed for SAP CPI/PI-PO compatibility. Error handling, monitoring, and retry logic framework available. Detailed configuration requires SAP environment access. | Technical Architecture Document | SAP CPI/PI-PO specific configuration requires access to Expertise SAP middleware environment for adapter setup and error monitoring. | Design integration architecture; configure SAP CPI adapters; implement error monitoring and alerting; conduct end-to-end testing. | Wk 12–16
GEO-FENCING & GPS TRACKING
80 | Section 3.5.8.1 / GF-01 | Build | Geo-fence definition for all vehicle categories (sites, depots, restricted zones) | Not Available | Geo-fence definition module supports polygon/radius-based geo-fences for project sites, offices, depots, pickup/drop locations, and restricted/high-risk zones across all vehicle categories. | Geo-fence Config Module – Application Demo | Integrate with GPS | Need to Integrate | Wk 10–13
81 | Section 3.5.8.1 / GF-02 | Build | Auto-trigger alerts (entry, exit, unauthorised deviation, time-based validation) | Not Available | Alert configuration supports auto-triggers on geo-fence entry, exit, unauthorized deviation, and time-based validation (early/delayed arrival) with multi-channel notification. | Geo-fence Alert Config – Demo | Integrate with SaudiEx | Need to Integrate | Wk 11–13
82 | Section 3.5.8.2 / GF-03 | Integration | GPS real-time tracking — live map view for transport admin | Not Available | Live map view framework available within the platform. Real-time GPS data display requires Saudi Ex GPS integration. |  | Real-time GPS vehicle location on live map requires Saudi Ex integration. | Integrate Saudi Ex GPS; configure live map view for transport admin; test real-time vehicle position updates. | Wk 13–16
83 | Section 3.5.8.2 / GF-04 | Build | Employee / passenger view — assigned vehicle, driver location & ETA | Not Available | Employee/passenger mobile view displays assigned vehicle details, driver location, and estimated arrival time for pickup/drop, reducing coordination calls. |  | Need to Develop | once GOS integration is done, this will be develped | Wk 14–16
84 | Section 3.5.8.3 / GF-05 | Build | Trip history logs (route, stops, deviations, duration) & audit replay | ⚠ Partially Available | Trip logging framework available. Full historical audit replay of GPS-tracked route, stops, deviations, and duration requires GPS integration data storage and replay feature development. | Trip Logging Module | GPS-based trip history replay requires Saudi Ex integration data retention and replay feature development. | Develop trip history storage from GPS feed; build audit replay feature with route visualization. | Wk 14–16
REPORTING, DASHBOARDS & ANALYTICS
85 | Section 3.7.1-A / RA-01 | Build | Management dashboard (fleet utilisation, costs, compliance, exceptions) | ✅ Fully Available | Management dashboard provides fleet utilization overview by category, cost per vehicle/route/project, compliance status summary, vendor vs owned performance, and exception alerts. | Management Dashboard – Application Demo | – | – | Wk 14–17
86 | Section 3.7.1-B / RA-02 | Build | Transport admin / operations dashboard (live GPS, availability, geo-fence alerts) | ⚠ Partially Available | Operations dashboard with availability, maintenance status, pending requests, and geo-fence violations available. Live GPS tracking requires Saudi Ex integration. | Operations Dashboard – Demo | Live GPS vehicle tracking on operations dashboard requires Saudi Ex GPS integration. | Integrate Saudi Ex GPS; configure live tracking on operations dashboard. | Wk 14–17
87 | Section 3.7.1-C / RA-03 | Build | HR / department dashboard (occupancy trends, allocation, eligibility compliance) | ✅ Fully Available | HR/Department dashboard displays employee transport utilization, seat occupancy trends, light vehicle allocation by department, and eligibility/policy compliance. | HR Dashboard – Application Demo | – | – | Wk 15–17
88 | Section 3.7.1-D / RA-04 | Build | Employee / passenger view dashboard (vehicle, driver, ETA) | ✅ Fully Available | Employee dashboard shows assigned vehicle and driver details, live pickup/drop tracking, and ETA visibility via mobile-friendly interface. | Employee Dashboard – Mobile Demo | – | – | Wk 15–17
89 | Section 3.7.2 / RA-05 | Build | Vehicle, driver, route & vendor KPI configuration | ✅ Fully Available | KPI configuration module covers all vehicle performance KPIs (utilization %, idle time, cost per km, maintenance cost, on-time %), driver KPIs (completion rate, violations), route efficiency KPIs, and vendor performance KPIs. | KPI Configuration Module – Demo | – | – | Wk 14–17
90 | Section 3.7.3 / RA-06 | Build | Vehicle capacity planner & utilisation optimiser | ✅ Fully Available | Capacity planning module covers seat capacity for buses, load capacity for heavy vehicles, forecasted vs actual utilization, and automatic recommendations for vehicle type, route consolidation, and trip merging. | Capacity Planner Module – Demo | – | – | Wk 15–18
91 | Section 3.7.4 / RA-07 | Build | Predictive & trend analytics (maintenance costs, demand forecasting) | ✅ Fully Available | Predictive analytics covers maintenance cost trend analysis, vehicle replacement recommendations, demand forecasting based on historical usage and project timelines, and seasonal demand analysis. | Analytics Module – Demo | – | – | Wk 16–19
92 | Section 3.7.5 / RA-08 | Integration | SAP-aligned financial & operational reports (cost centre, project/WBS, vendor) | Not Available | Operational reports available within the platform. SAP-aligned financial reports (cost center, WBS, vendor reconciliation) require SAP integration data feeds. | Reports Module; SAP Integration Spec | SAP financial data alignment for cost center/WBS reports requires SAP integration to be completed first. | Deliver SAP-aligned financial reports post SAP integration completion; configure report templates per Expertise chart of accounts. | Wk 16–19
93 | Section 3.7.2 / RA-09 | Build | Power BI export / read-only KPI exposure | ⚠ Partially Available | Excel/PDF export available. Power BI read-only KPI exposure via REST API or OData feed requires configuration of BI connector. | Reports Module | Power BI integration requires OData/REST API connector configuration for read-only KPI exposure. | Configure BI connector (OData/REST); validate Power BI connectivity with sample KPI dataset. | Wk 17–19
94 | Section 3.7.6 / RA-10 | Build | Report scheduling, drill-down & audit-ready reporting logs | ✅ Fully Available | Reporting module supports scheduled report distribution, drill-down from dashboard to transaction, multi-period comparison, export to Excel/PDF, and audit-ready reporting logs. | Reporting Module – Demo | – | – | Wk 16–19
95 | Section 3.7.3 / RA-11 | Build | What-if simulation — demand scenarios (peak/off-peak, fleet optimization) | ✅ Fully Available | What-if simulation module supports peak vs off-peak demand scenarios, fleet size optimization, and underutilized vehicle/overloaded assignment alerts. | Simulation Module – Demo | – | – | Wk 16–19
WORKFLOW BUILDER & APPROVAL FRAMEWORK
96 | Section 3.9.1 / WF-01 | Build | No-code / low-code workflow designer setup & configuration | ⚠ Partially Available | Visual workflow builder with configurable approval steps, conditions, and SLA rules available. Drag-and-drop no-code designer interface requires development/enhancement for full no-code capability. | Workflow Builder Module – Demo | Full drag-and-drop no-code workflow designer interface requires development/enhancement. | Develop enhanced no-code workflow designer UI; validate with Expertise workflow requirements. | Wk 8–10
97 | Section 3.9.2-A / WF-02 | Build | Transport request & allocation approval workflows (bus, light, heavy) | ✅ Fully Available | Approval workflows configured for all transport request types (bus allocation, light vehicle request, heavy vehicle movement) with role-based routing, parallel/sequential steps, and SLA escalation. | Workflow Builder – Transport Approval Config Demo | – | – | Wk 9–12
98 | Section 3.9.2-B / WF-03 | Build | Vehicle & asset lifecycle workflows (onboarding, decommission, ownership change) | ✅ Fully Available | Asset lifecycle workflows cover vehicle onboarding, decommissioning, ownership change (owned ↔ vendor), and temporary reassignment with full approval and audit trail. | Asset Lifecycle Workflow Config – Demo | – | – | Wk 9–12
99 | Section 3.9.2-C / WF-04 | Build | Employee & driver-related workflows (assignment, eligibility, licence expiry) | ✅ Fully Available | Driver assignment, eligibility validation, and license expiry exception handling workflows configured with approval routing and automated alert triggers. | Driver Workflow Config – Demo | – | – | Wk 10–12
100 | Section 3.9.2-D / WF-05 | Build | Vendor & RFQ approval workflows (RFQ, vendor selection, rate card) | ✅ Fully Available | Vendor and RFQ workflows cover RFQ approval, vendor selection, rate card approval, and exception cost approval with multi-level routing. | Vendor/RFQ Workflow Config – Demo | – | – | Wk 10–12
101 | Section 3.9.2-E / WF-06 | Build | Policy & exception handling workflows (geo-fence, out-of-policy, grade overrides) | ⚠ Partially Available | Grade override and out-of-policy workflows available. Geo-fence violation review and route deviation approval workflows require development. | Exception Workflow Config | Geo-fence violation review workflow and route deviation approval workflow require development. | Develop geo-fence violation review and route deviation approval workflows; configure escalation rules. | Wk 11–13
102 | Section 3.9.3 / WF-07 | Integration | SAP org structure & cost centre approval routing | Not Available | Cost center routing available within platform. SAP organizational structure-derived approver routing requires SAP org structure integration. | Workflow Config; SAP Integration Spec | SAP org structure-derived approver routing requires SAP HCM integration for org hierarchy data. | Integrate SAP org structure; configure workflow routing rules based on SAP cost center hierarchy. | Wk 13–15
103 | Section 3.9.4 / WF-08 | Build | Multi-channel notification config (in-app, email, SMS) | ✅ Fully Available | Multi-channel notifications configured for in-app, email, and SMS (configurable). Approval actions include Approve, Reject, Request Clarification with delegation and substitution. | Notification Config Module – Demo | – | – | Wk 12–14
104 | Section 3.9.5 / WF-09 | Build | Workflow audit trail, SLA breach tracking & version control | ✅ Fully Available | Complete audit trail of workflow configuration changes and approval decisions. Time-stamped approvals, SLA breach tracking, compliance reporting, and workflow version control. | Workflow Audit Module – Demo | – | – | Wk 13–15
TECHNICAL & NON-FUNCTIONAL
105 | Section 3.10 / TN-01 | Build | Cloud architecture setup, HA & DR configuration | ✅ Fully Available | Solution deployed on cloud-ready architecture with high availability (99.9% uptime SLA), disaster recovery configuration, and environment segregation (DEV/UAT/PROD). | Technical Architecture Document | – | – | Wk 4–7
106 | Section 3.11.4 / TN-02 | Build | DEV / UAT / PROD environment segregation | ✅ Fully Available | Three separate environments (DEV, UAT, PROD) maintained throughout the project with controlled promotion process and environment-specific access controls. | Environment Setup Guide | – | – | Wk 4–6
107 | Section 3.11.5 / TN-03 | Build | Role-based access control (RBAC) implementation | ✅ Fully Available | RBAC implemented across all modules with role definitions for Transport Admin, Fleet Manager, Driver, Employee, HR, Finance, and Executive roles. Workflow visibility controlled by role. | RBAC Config Module – Application Demo | – | – | Wk 8–10
108 | Section 3.11.5 / TN-04 | Build | Security — data encryption, RBAC, vulnerability assessment | ✅ Fully Available | Data encryption in transit (TLS 1.2+) and at rest. RBAC enforced across all modules. Regular vulnerability assessments and penetration testing conducted per industry standards. | Security Architecture Document | – | – | Wk 8–12
109 | Section 3.11.2 / TN-05 | UAT | UAT scripts preparation & execution | ✅ Fully Available | UAT scripts covering all functional scenarios prepared in Design phase and executed during UAT with defect tracking, resolution, and sign-off process. | UAT Script Template; Test Management Tool | – | – | Wk 20–23
110 | Section 3.11.4 / TN-06 | UAT | Performance & scalability testing | ✅ Fully Available | Performance testing conducted to validate response times, concurrent user load, and scalability requirements. Bottlenecks identified and resolved before go-live. | Performance Test Plan | – | – | Wk 20–22
111 | Section 3.6.1 / TN-07 | UAT | Mobile-friendly UI validation | ✅ Fully Available | Application UI validated for mobile responsiveness across iOS and Android devices. Driver and employee-facing views optimized for mobile usage. | Mobile UI Test Plan; Device Test Results | – | – | Wk 20–22
112 | Section 3.11.1 / TN-08 | UAT | Issue resolution log & root cause analysis (UAT) | ✅ Fully Available | Issue resolution log maintained throughout UAT with defect classification, root cause analysis, fix validation, and closure documentation. | Issue Log / Defect Tracking Tool | – | – | Wk 21–24
DOCUMENTATION
113 | Section 3.11.2 / DO-01 | Design | Business blueprint (AS-IS & TO-BE processes) | ✅ Fully Available | Business blueprint document covers all AS-IS process documentation and TO-BE process design across all T&L modules agreed with Expertise stakeholders. | Business Blueprint Document Template | – | – | Wk 4–7
114 | Section 3.11.2 / DO-02 | Build | Configuration manuals & WRICEF functional/technical specifications | ✅ Fully Available | Configuration manuals and WRICEF (Workflow, Reports, Interfaces, Conversions, Enhancements, Forms) functional/technical specifications prepared for all custom objects. | Configuration Manual Template | – | – | Wk 14–18
115 | Section 3.11.2 / DO-03 | Integration | Integration documentation (SAP, GPS, ZKT, Petro APP) | ✅ Fully Available | Integration documentation covers all interface specifications, API mapping, data flow diagrams, error handling, and monitoring for SAP, GPS, ZKT, and Petro APP integrations. | Integration Specification Template | – | – | Wk 15–18
116 | Section 3.11.3 / DO-04 | UAT | User manuals & role-specific guides | ✅ Fully Available | User manuals and role-specific quick reference guides prepared for all user roles: Transport Admin, Fleet Manager, Driver, Employee, HR, Finance, and Management. | User Manual Template | – | – | Wk 20–22
117 | Section 3.11.3 / DO-05 | UAT | Video tutorials & quick reference guides | ✅ Fully Available | Video tutorials and quick reference guides prepared for key user scenarios covering request submission, approval, allocation, compliance, and reporting. | Training Material Templates | – | – | Wk 21–23
118 | Section 3.11.2 / DO-06 | UAT | AMS operational documents (escalation matrix, issue resolution workflows) | ✅ Fully Available | AMS operational documentation covers support escalation matrix, issue resolution workflows, SLA definitions, and incident management process. | AMS Operational Document Template | – | – | Wk 22–24
119 | Section 3.11.2 / DO-07 | Go-Live | Go-live & post-go-live cutover / stabilisation plan | ✅ Fully Available | Go-live cutover plan covers pre-go-live checklist, cutover sequence, go/no-go criteria, rollback plan, and post-go-live stabilization activities and support structure. | Go-Live Plan Template | – | – | Wk 24–25
120 | Section 3.11.2 / DO-08 | UAT | Change management documentation | ✅ Fully Available | Change management documentation covers stakeholder impact assessment, communication plan, training needs analysis, adoption metrics, and change champion identification. | Change Management Document Template | – | – | Wk 22–24
121 | Section 2.4 / DO-09 | Inception | Weekly status report template & progress tracking process | ✅ Fully Available | Weekly status report template covers milestone progress, risk register update, issue log, action items, and next week plan. Distributed to all stakeholders. | Status Report Template | – | – | Inception – Continuous
TRAINING, GO-LIVE & POST GO-LIVE
122 | Section 3.11.3 / TG-01 | UAT | Train-the-trainer sessions | ✅ Fully Available | Train-the-trainer program equips key Expertise users to independently train end users. Covers all modules with hands-on practice sessions and Q&A. | Training Plan; TTT Session Materials | – | – | Wk 22–24
123 | Section 3.11.3 / TG-02 | UAT | End-user training — functional & technical | ✅ Fully Available | Role-based end-user training sessions covering all functional and technical aspects for each user group with hands-on system walkthroughs. | Training Plan; Training Materials | – | – | Wk 23–25
124 | Section 3.11.3 / TG-03 | Go-Live | Post-go-live workshops & adoption review | ✅ Fully Available | Post-go-live workshops conducted to address user challenges, review adoption metrics, and identify optimization opportunities. Lessons learned documented. | Post-Go-Live Workshop Plan | – | – | Wk 28–30
125 | Section 3.11.2 / TG-04 | Go-Live | Cut-over / go-live execution & hypercare | ✅ Fully Available | Go-live execution managed per cutover plan with dedicated hypercare team providing on-site and remote support during the critical stabilization period. | Cutover Plan; Hypercare Support Plan | – | – | Wk 26
126 | Section 2.4 / TG-05 | Go-Live | Post go-live stabilisation support (2 months) | ✅ Fully Available | 2-month post-go-live stabilization support provided with dedicated support team, issue tracking, priority resolution, and weekly review meetings. | Post-Go-Live Support SLA | – | – | Wk 27–34
127 | Section 2.4 / TG-06 | Go-Live | Lessons learned & final project closure report | ✅ Fully Available | Lessons learned workshop conducted and final project closure report prepared covering achievements vs plan, key learnings, recommendations, and formal project sign-off. | Project Closure Report Template | – | – | Wk 33–34
128 | Section 3.11.2 / TG-07 | Support | AMS SLA performance report & issue resolution log | ✅ Fully Available | Monthly AMS SLA performance reports cover ticket volume, resolution times, SLA compliance, root cause analysis, and system optimization records. | AMS SLA Reporting Template | – | – | Support – Continuous

## Sheikh
Expertise Company – T&L Implementation: Fit-Gap Analysis Matrix
Fit Status Legend: ✅ Fully Available ¦ ⚠ Partially Available ¦ ❌ Not Available
# | RFP Section / Requirement Reference | Phase | Requirement Description | Fit Status | Solution Description (How the requirement is addressed) | Reference Evidence (Document / Screen / Demo Ref) | Gap Description (If Applicable) | Proposed Approach to Address Gap | Suggested Timeline
PROJECT GOVERNANCE & KICK-OFF
1 | Section 2.4 / PG-01 | Inception | Project charter & communication plan | ✅ Fully Available | Our solution delivery methodology includes a standard project charter template, RACI matrix, and structured communication plan prepared at project inception. | Implementation Methodology Document | – | – | Wk 1–2
2 | Section 2.4 / PG-02 | Inception | Roles & responsibilities matrix (RACI) | ✅ Fully Available | A RACI matrix covering all project workstreams — functional, integration, technical, and testing — is prepared and agreed during the inception phase. | Project Governance Template | – | – | Wk 1–2
3 | Section 2.4 / PG-03 | Inception | Risk register & mitigation plan | ✅ Fully Available | Risk register maintained throughout the project with proactive identification, classification, impact assessment, and mitigation actions reviewed weekly. | Risk Register Template | – | – | Wk 2–3
4 | Section 2.4 / PG-04 | Inception | Governance framework & escalation matrix | ✅ Fully Available | Governance framework defines steering committee, project sponsor, workstream leads, and escalation paths with defined SLA for issue resolution. | Governance Framework Document | – | – | Wk 2
5 | Section 2.4 / PG-05 | Inception | Detailed project plan with milestones | ✅ Fully Available | Full project plan covering all phases — Inception, Design, Build, Integration, UAT, Go-Live, and Hypercare — with milestone-based delivery tracked in project management tool. | Project Plan / MS Project / Jira | – | – | Wk 2–3
MASTER DATA MANAGEMENT
6 | Section 3.8.2-A / MDM-01 | Design | Location & geo master (sites, depots, pickup/drop, geo-fence) | ✅ Fully Available | Application supports full location master setup including project sites, depots, pickup/drop points, and geo-fence polygon definitions linked to GPS coordinates. | Application Master Data Module – Demo Screen MDM-01 | – | – | Wk 5–7
7 | Section 3.8.2-B / MDM-02 | Design | Route master (ID, origin, destination, stops, distance) | ✅ Fully Available | Route master configuration supports route ID, origin/destination, intermediate stops, distance, estimated time, and compliance flags. | Application Route Master Config Screen | – | – | Wk 5–7
8 | Section 3.8.2-C / MDM-03 | Design | Compliance & document master (types, authority, validity, alerts) | Partially Availabl | Document master supports all document types (Registration, Insurance, Permit, License), issuing authority, validity period, alert thresholds, and KSA regulatory categories. | Document repository is available - Demo | – | – | Wk 5–7
9 | Section 3.8.5-B / MDM-04 | Design | Light vehicle master & employee eligibility master | ✅ Fully Available | Light vehicle master includes vehicle class, model level (M1/M2/M3), eligibility grade mapping, ownership type, GPS tag, and status. Employee eligibility master links grade to vehicle type with approval authority. | Light Vehicle Master – Application Config | – | – | Wk 6–8
10 | Section 3.8.3-A,B,C / MDM-05 | Design | Bus master, driver & passenger/employee mapping master | ✅ Fully Available | Bus master includes Bus ID (linked to SAP Equipment No.), seating capacity, GPS device ID, ownership. Driver master includes license category, shift eligibility. Passenger mapping links employees to routes and pickup points. | Bus Management Master Data Screens | – | – | Wk 6–8
11 | Section 3.8.4-A / MDM-06 | Design | Heavy vehicle / equipment & permit master | ✅ Fully Available | Equipment master covers trucks, trailers, low-beds, cranes with load capacity, axle details, compliance profile (MIZAN, TAMM), GPS tag, and vendor association. Permit master covers permit type, valid routes, and load restrictions. | Heavy Vehicle Master Data Module | – | – | Wk 6–8
12 | Section 3.8.6 / MDM-07 | Design | Maintenance & condition master (SAP PM aligned) | Partially Available | Maintenance master supports maintenance category, breakdown type, service schedule, and vehicle condition codes. Need to be Aligned with SAP PM for bi-directional status synchronization. | Maintenance Master | – | – | Wk 6–8
13 | Section 3.8.7 / MDM-08 | Build | Data quality controls — duplicate prevention, field validation, reconciliation | ✅ Fully Available | Platform enforces mandatory field validation, duplicate prevention rules, periodic master data reconciliation with SAP, | Data Quality Controls Config – Application Admin | – | – | Wk 9–11
LIGHT VEHICLE MANAGEMENT
14 | Section 3.4.1 / LV-01 | Design | AS-IS process documentation | ✅ Fully Available | Business analyst workshops conducted to document current state processes for all light vehicle operations including allocation, return, and compliance tracking. | Business Blueprint Document – Phase 1 Design | – | – | Wk 3–5
15 | Section 3.4.1 / LV-02 | Design | TO-BE process / business blueprint | ✅ Fully Available | TO-BE process design maps all optimized workflows for light vehicle request, approval, allocation, return, and compliance aligned with T&L platform capabilities. | Business Blueprint – TO-BE Process Design | – | – | Wk 4–6
16 | Section 3.4.1 / LV-03 | Build | Vehicle request config (permanent, temporary, one-time/trip-based) | ✅ Fully Available | Application supports three vehicle request types: permanent allocation, temporary allocation, and one-time/trip-based requests — each with distinct approval paths and policy controls. | Vehicle Request Module – Demo / Config Screens | – | – | Wk 7–10
17 | Section 3.4.1 / LV-04 | Build | Vehicle request approval workflow | ✅ Fully Available | Approval workflows configured per request type, role, grade, and policy. Supports parallel/sequential approvals, SLA tracking, and delegation. | Workflow Builder – Light Vehicle Approval Config | – | – | Wk 7–10
18 | Section 3.4.1 / LV-05 | Build | Vehicle allocation | ✅ Fully Available | Manual and system-assisted vehicle allocation based on request type, availability, and policy. Allocation linked to cost center and department. | Vehicle Allocation Module – Application Demo | – | – | Wk 7–10
19 | Section 3.4.1 / LV-06 | Build | Smart / intelligent auto-allocation | ⚠ Partially Available | Recommendation engine available. Auto-allocation logic can suggest vehicles based on availability, location, and utilization history. Full AI-driven auto-assignment requires configuration and tuning to client-specific rules. | Intelligent Allocation Module – Demo | Full autonomous auto-allocation requires rule configuration and testing for grade eligibility, owned vs. leased preference, and shift-based demand. | Configure recommendation engine rules; build preference logic for owned-first allocation; test and validate with Expertise data. | Wk 16–19
20 | Section 3.4.1 / LV-07 | Build | Vehicle pool & grade eligibility setup (M1/M2/M3) | ✅ Fully Available | Vehicle pool module supports grade-based eligibility (M1, M2, M3) mapped to vehicle categories (SUV, Sedan, Small SUV) with HR exception approval workflow. | Vehicle Pool Config – Grade Eligibility Mapping | – | – | Wk 7–10
21 | Section 3.4.1 / LV-08 | Build | Owned vs leased vehicle segregation logic | ✅ Fully Available | Platform maintains clear ownership type flags (Owned / Vendor-Leased) on all vehicles. Allocation logic prioritizes owned fleet. Reports and dashboards display segregated views. | Vehicle Master – Ownership Config; Fleet Dashboard | – | – | Wk 8–10
22 | Section 3.4.1 / LV-09 | Build | Intelligent allocation & recommendation engine config | ⚠ Partially Available | Recommendation engine considers vehicle availability, current location, utilization history, and upcoming demand. Configuration required to tune client-specific allocation preferences. | Recommendation Engine Config Module | Engine parameters need tuning for Expertise-specific rules including grade restrictions, project-location preferences, and owned-vehicle priority. | Configure and calibrate recommendation engine parameters with Expertise operational data; validate outputs with transport admin. | Wk 9–12
23 | Section 3.4.1 / LV-10 | Build | Breakdown & maintenance alert workflows | ✅ Fully Available | Breakdown reporting triggers automatic alerts to maintenance teams. Notification workflows configurable via workflow builder. Repair checklist and maintenance history tracked per vehicle. | Breakdown Alert Workflow – Application Demo | – | – | Wk 10–12
24 | Section 3.4.1 / LV-11 | Build | Document & compliance management (Insurance, Istimara) | ✅ Fully Available | All vehicle documents (Insurance, Istimara, ownership records, transfer history) managed centrally with expiry alerts, compliance dashboards, and audit trail. | Document Management Module – Application Demo | – | – | Wk 10–12
25 | Section 3.4.1 / LV-12 | Integration | Financial cross-charge & vendor invoicing integration (SAP MM/CO) | ⚠ Partially Available | Integration framework supports financial postings and cross-charge to requesting department/cost center. SAP MM/CO integration for vendor invoicing requires configuration of SAP CPI/PI-PO middleware. | Integration Architecture Document | SAP MM/CO integration requires API mapping, SAP CPI configuration, and testing with Expertise SAP environment. | Design integration specs; configure SAP CPI adapters; conduct integration testing with Expertise SAP S/4HANA system. | Wk 13–16
26 | Section 3.4.1 / LV-13 | Build | Ownership tracking — ownership transfer records | ✅ Fully Available | Vehicle master maintains full ownership history including current and previous owners, transfer records, and handover dates with complete audit trail. | Vehicle Ownership History – Application Screen | – | – | Wk 7–10
27 | Section 3.4.1 / LV-14 | Build | HR exception approval workflow for grade eligibility overrides | ✅ Fully Available | Exception workflow supports HR approval for grade eligibility overrides with justification capture, multi-level approval, and policy documentation. | Exception Workflow Config – Application Demo | – | – | Wk 7–10
BUS MANAGEMENT (EMPLOYEE TRANSPORTATION)
28 | Section 3.4.2 / BM-01 | Build | Bus master data & seating capacity setup | ✅ Fully Available | Bus master includes Bus ID (SAP Equipment No. linked), make/model, seating capacity, plate number, ownership type, GPS device ID, vendor reference, and operational status. | Bus Master Data Config – Application Demo | – | – | Wk 7–9
29 | Section 3.4.2 / BM-02 | Build | Route planning & pickup/drop point configuration | ✅ Fully Available | Route planning module supports full route definition with pickup/drop points, distance, estimated time, shift-based assignment, and period-based allocation (weekly/monthly). | Route Planning Module – Application Demo | – | – | Wk 8–11
30 | Section 3.4.2 / BM-03 | Build | Shift-based daily trip planning automation | ⚠ Partially Available | Shift-based trip planning framework is available. Full automation of daily trip plans based on SAP roster and leave data requires development of automated scheduling engine. | Trip Planning Module – Partial Demo | Automated daily schedule generation based on real-time SAP roster/leave data requires development of scheduling automation logic. | Develop automated trip scheduling engine integrated with SAP roster feed; configure shift-to-route mapping; validate with Expertise shift patterns. | Wk 9–12
31 | Section 3.4.2 / BM-04 | Integration | SAP roster & leave integration (auto-exclusion from schedules) | ⚠ Partially Available | Integration framework supports SAP HCM/SuccessFactors connectivity. Auto-exclusion of employees on leave from pickup/drop schedules and dynamic route adjustment requires integration development. | Integration Architecture – SAP Roster | SAP roster and leave integration API mapping, real-time sync, and auto-exclusion logic requires integration development and testing. | Develop SAP CPI integration for roster/leave feed; implement auto-exclusion rule engine; validate with Expertise SAP environment. | Wk 13–15
32 | Section 3.4.2 / BM-05 | Build | Intelligent route optimisation & consolidation | ⚠ Partially Available | Route optimization capability identifies low-occupancy routes and provides consolidation recommendations based on origin/destination, shift timing, planned occupancy, and route distance. | Route Optimization Module – Partial Demo | Full route optimization engine requires configuration of consolidation thresholds and validation with Expertise route data. | Configure consolidation rules and occupancy thresholds; implement route consolidation recommendation engine; validate outputs. | Wk 16–19
33 | Section 3.4.2 / BM-06 | Build | Geo-fence violation alerts & off-day operation controls | ⚠ Partially Available | Geo-fence alert framework is available. Integration with GPS (Saudi Ex) required for real-time violation detection. Off-day operation control alerts require GPS integration. | Geo-fence Module; GPS Integration Spec | Requires GPS (Saudi Ex) integration for real-time geo-fence violation detection and alert triggering. | Integrate Saudi Ex GPS feed; configure geo-fence zones; implement violation alert rules and notification workflows. | Wk 11–13
34 | Section 3.4.2 / BM-07 | Build | Bus compliance document management (MIZAN, Istimara, Insurance) | Not Available | Document management framework supports insurance and Istimara. MIZAN-specific permit type and KSA regulatory compliance category requires additional configuration and development. | Document Management Module | MIZAN permit type configuration and KSA-specific regulatory category requires development for bus compliance. | Develop MIZAN document type and compliance category; integrate expiry alerts and compliance dashboard for bus fleet. | Wk 10–12
35 | Section 3.4.2 / BM-08 | Integration | Financial cross-charge to departments/projects via SAP | Not Available | Financial cross-charge framework available within the platform. SAP CO/PS integration for automated posting to cost centers and projects requires SAP CPI configuration. | Financial Integration Spec | SAP CO/PS integration for cross-charge posting requires API design, SAP CPI configuration, and testing. | Design and configure SAP CO/PS integration via SAP CPI; test cross-charge postings with Expertise SAP environment. | Wk 13–16
36 | Section 3.4.2 / BM-09 | Build | Period-based bus allocation (weekly/monthly planning) | ✅ Fully Available | Bus allocation module supports period-based planning (weekly, monthly) with capacity tracking, route assignment, and scheduled occupancy visibility. | Bus Period Allocation Config – Application Demo | – | – | Wk 10–13
HEAVY VEHICLE & EQUIPMENT MANAGEMENT
37 | Section 3.4.3 / HV-01 | Build | Equipment master data setup (trucks, trailers, low-beds, cranes) | ✅ Fully Available | Equipment master covers all heavy vehicle categories (trucks, trailers, low-beds, cranes, heavy equipment) with full attributes including load capacity, axle details, compliance profile, and ownership. | Equipment Master Data Module – Application Demo | – | – | Wk 7–9
38 | Section 3.4.3 / HV-02 | Build | Transport request & approval workflow (35–40+ daily requests) | ✅ Fully Available | Transport request module handles high-volume daily requests with configurable approval workflows, priority handling, and automated routing based on vehicle type and request attributes. | Heavy Vehicle Request Module – Demo | – | – | Wk 8–11
39 | Section 3.4.3 / HV-03 | Build | Transport vehicle request approval workflow | ✅ Fully Available | Multi-level approval workflow for heavy vehicle requests with configurable approval steps, parallel/sequential routing, and SLA-based escalation. | Workflow Builder – Heavy Vehicle Approval Config | – | – | Wk 8–11
40 | Section 3.4.3 / HV-04 | Build | Transport vehicle auto-allocation / suggestion | ✅ Fully Available | System provides vehicle suggestion based on load requirements, route constraints, permit requirements, current availability, and compliance readiness. | Vehicle Suggestion Engine – Application Demo | – | – | Wk 8–11
41 | Section 3.4.3 / HV-05 | Build | Automatic data population based on requestor's mobilization and department | ✅ Fully Available | Request form auto-populates employee details (department, cost center, project/WBS, location) from SAP Employee Master integration upon requester identification. | Auto-Population Config – Request Form Demo | – | – | Wk 8–11
42 | Section 3.4.3 / HV-06 | Build | Auto form filling | ✅ Fully Available | Smart form auto-fills requester details, department, cost center, project code, and location fields based on SAP employee data reducing manual entry and errors. | Smart Form Config – Application Demo | – | – | Wk 8–11
43 | Section 3.4.3 / HV-07 | Build | Intelligent vehicle recommendation engine (load, route, availability) | ✅ Fully Available | Recommendation engine evaluates vehicle suitability based on load weight, dimensions, route constraints, permit requirements, current availability, and real-time GPS location. | Recommendation Engine – Heavy Vehicle Demo | – | – | Wk 10–13
44 | Section 3.4.3 / HV-08 | Build | KSA regulatory compliance setup (MIZAN, TAMM, MVPI, Tasriya, Naql) | Not Available | Compliance profile framework is available on the equipment master. KSA-specific regulatory categories (MIZAN, TAMM, MVPI, Tasriya, Naql) require development of compliance rule sets and permit validation workflows. | Equipment Master – Compliance Profile | KSA regulatory compliance categories and permit validation workflows require specific development for MIZAN, TAMM, MVPI, Tasriya, and Naql requirements. | Design and develop KSA compliance rule set for each regulatory category; build permit validation engine; integrate with regulatory alert workflows. | Wk 10–13
45 | Section 3.4.3 / HV-09 | Build | Permit validation prior to dispatch | ✅ Fully Available | System validates all required permits against equipment compliance profile before allowing dispatch confirmation. Invalid or expired permits trigger blocking alerts. | Permit Validation – Pre-Dispatch Check Demo | – | – | Wk 11–13
46 | Section 3.4.3 / HV-10 | Build | Vendor RFQ creation, bid comparison & assignment workflow | ⚠ Partially Available | RFQ framework supports vendor invitation and bid collection. Full bid comparison matrix and vendor selection workflow require development. | Vendor RFQ Module – Partial Demo | Structured bid comparison matrix and automated vendor scoring/selection workflow require development. | Develop bid comparison module and vendor selection workflow; integrate with vendor master and rate card master. | Wk 9–12
47 | Section 3.4.3 / HV-11 | Integration | Trip execution monitoring & GPS-based tracking | Not Available | Trip execution milestone tracking available within the platform. Real-time GPS tracking requires integration with Saudi Ex GPS system. | Trip Monitoring Module; GPS Integration Spec | GPS-based real-time trip tracking requires Saudi Ex integration development. | Develop Saudi Ex GPS integration; configure real-time trip status update; implement geo-visibility on live map. | Wk 13–16
48 | Section 3.4.3 / HV-12 | Build | Proof of delivery (driver/vendor upload) & trip completion | ✅ Fully Available | Proof of delivery supports document/photo upload by driver or vendor. Trip completion confirmation triggers workflow and SAP cost posting. | Driver photo clicking demo shown | – | – | Wk 11–13
49 | Section 3.4.3 / HV-13 | Integration | SAP PS/CO integration for project-based costing | Not Available | Integration framework available. SAP PS/CO integration for project-based cost allocation requires SAP CPI configuration, WBS mapping, and end-to-end testing. | SAP Integration Architecture | SAP PS/CO integration requires API design, SAP CPI configuration, WBS/project mapping, and testing with Expertise SAP environment. | Design SAP PS/CO integration specs; configure SAP CPI; test project-based cost posting with Expertise system. | Wk 14–17
50 | Section 3.4.3 / HV-14 | Build | Equipment availability forecasting (release & next availability) | ✅ Fully Available | Equipment availability module tracks current assignments, planned maintenance, and estimated release dates providing next availability forecasting for planning. | Equipment Availability Dashboard – Demo | – | – | Wk 16–19
DRIVER MANAGEMENT
51 | Section 3.4.4 / DM-01 | Build | Centralised driver master data (owned & vendor drivers) | ✅ Fully Available | Single driver master covers owned and vendor drivers with full profile including Employee ID (SAP), license category, Iqama, insurance, and current/historical assignment. | Driver Master Module – Application Demo | – | – | Wk 7–9
52 | Section 3.4.4 / DM-02 | Build | Document management (license, Iqama, insurance) & expiry alerts | ✅ Fully Available | Driver document management covers driving license (issue/expiry), Iqama, and insurance with automated expiry alerts, compliance dashboards, and audit trail. | Driver Document Management – Demo | – | – | Wk 8–11
53 | Section 3.4.4 / DM-03 | Build | Driver utilisation & availability tracking (trips, idle time, absenteeism) | Partially Available. | Driver utilization module tracks trips completed, idle vs active time, and absenteeism linked to SAP roster/leave data. | Driver Utilization Dashboard – Demo | SAP Integration Required | – | Wk 9–12
54 | Section 3.4.4 / DM-04 | Build | Driver communication | ✅ Fully Available | In-app messaging and notification system enables direct communication with drivers for trip assignments, schedule changes, alerts, and emergency notifications. | Driver Communication Module – Demo | – | – | Wk 9–12
55 | Section 3.4.4 / DM-05 | Build | Driver dashboard | ✅ Fully Available | Role-based driver dashboard displays today's assignments, trip status, document expiry alerts, and performance KPIs accessible via mobile-friendly interface. | Driver Dashboard – Mobile Demo | – | – | Wk 9–12
56 | Section 3.4.4 / DM-06 | Build | Driver trip logging | ✅ Fully Available | All driver trips logged with start/end time, route taken, distance, stops, deviations, and trip status. Linked to vehicle GPS data for audit trail. | Trip Logging Module – Application Demo | – | – | Wk 9–12
57 | Section 3.4.4 / DM-07 | Build | Performance & safety insights (violations, on-time rate, completion rate) | ✅ Fully Available | Driver performance analytics covers safety violations (from GPS), on-time pickup/drop %, route deviation count, trip completion rate, and incident frequency. | Driver Performance Analytics – Demo | – | – | Wk 10–13
58 | Section 3.4.4 / DM-08 | Integration | SAP Employee Master & roster integration | Not Available | Integration framework supports SAP HCM/SuccessFactors connectivity. Employee and driver master sync, roster, shift, and leave integration requires SAP CPI configuration. | SAP Integration Architecture | SAP Employee Master and roster integration requires API design, SAP CPI configuration, and testing. | Design SAP HCM/SuccessFactors integration specs; configure SAP CPI; validate driver/employee master sync with Expertise SAP. | Wk 13–15
VEHICLE VIOLATIONS & COMPLIANCE
59 | Section 3.4.5 / VC-01 | Build | Violation capture config (speeding, geo-fence breach, doc non-compliance) | Partially Available | Violation capture module configured for speeding, route deviation, geo-fence breach, and document non-compliance. Manual entry and GPS-triggered violations supported. | Violation Capture Config – Application Demo | – | – | Wk 9–12
60 | Section 3.4.5 / VC-02 | Integration | Multi-source violation ingestion (GPS, manual entry, govt portal) | Not Available | Manual entry and GPS-based violations supported. Government portal reference ingestion requires integration development. | Violation Ingestion Module | Government portal integration for automated violation ingestion requires API development. | Develop government portal integration or manual import workflow for government-issued violation references. | Wk 13–15
61 | Section 3.4.5 / VC-03 | Build | Violation lifecycle management (reported → under review → resolved) | ⚠ Partially Available | Violation status tracking partially available. Full lifecycle management including Disputed status and structured resolution workflow requires development. | Violation Module – Partial Demo | Disputed status handling and structured lifecycle workflow (Reported → Under Review → Disputed → Resolved/Closed) requires development. | Develop complete violation lifecycle workflow with all status transitions, approval steps, and audit trail. | Wk 10–12
62 | Section 3.4.5 / VC-04 | Build | Financial & disciplinary linkage (cost allocation, vendor penalties, driver record) | ⚠ Partially Available | Driver record linkage available. Financial cost allocation to department/project and vendor penalty processing require development and SAP integration. | Driver Records Module | Financial linkage for department cost allocation and vendor penalty processing requires development and SAP CO integration. | Develop financial linkage module for violation cost allocation; integrate vendor penalty workflow with SAP MM. | Wk 11–13
VENDOR & RFQ MANAGEMENT
63 | Section 3.5.4 / VR-01 | Integration | Vendor master data setup & SAP MM integration | ⚠ Partially Available | Vendor master data management available within the platform. SAP MM integration for vendor master sync requires SAP CPI configuration. | Vendor Master Module; SAP Integration Spec | SAP MM integration for vendor master synchronization requires API design and SAP CPI configuration. | Design SAP MM vendor master integration; configure SAP CPI adapter; test bi-directional sync. | Wk 12–15
64 | Section 3.4.3 / VR-02 | Build | RFQ creation, vendor invitation & bid comparison workflow | ⚠ Partially Available | RFQ creation and vendor invitation framework available. Structured bid comparison matrix and vendor scoring workflow require development. | RFQ Module – Partial Demo | Bid comparison matrix and automated vendor scoring/selection workflow require development. | Develop bid comparison and vendor selection modules; build approval workflow for vendor award. | Wk 9–12
65 | Section 3.8.4-D / VR-03 | Build | Rate card master (trip-based / KM-based pricing, validity period) | ⚠ Partially Available | Rate card master supports trip-based and KM-based pricing models with validity periods, vendor-specific rates, and contract references. |  | Development | Will be developed based on user inputs | Wk 10–12
66 | Section 3.7.2.4 / VR-04 | Build | Vendor performance KPI tracking (SLA, cost variance, invoice accuracy) | ✅ Fully Available | Vendor performance dashboard tracks SLA compliance %, cost variance vs contract, service rejection/failure rate, compliance adherence, and invoice accuracy rate. | Vendor Performance Dashboard – Demo | – | – | Wk 12–15
SAP S/4HANA INTEGRATION
67 | Section 3.5.1 / SI-01 | Integration | Employee & driver master integration (HCM / SuccessFactors) | Not Available | Integration framework and API connectors available. SAP HCM/SuccessFactors employee and driver master sync requires SAP CPI configuration and testing with Expertise environment. | SAP Integration Architecture Document | Requires SAP CPI configuration, API mapping, and testing with Expertise SAP HCM/SuccessFactors. | Design integration specs; configure SAP CPI; develop field mapping; conduct integration testing. | Wk 11–14
68 | Section 3.5.2 / SI-02 | Integration | Employee roster, shift & leave integration | Not Available | Roster and leave integration framework available. Auto-exclusion logic and dynamic route adjustment require integration development and testing. | SAP Integration Architecture | Real-time roster/leave sync and auto-exclusion logic require SAP CPI integration development. | Develop SAP CPI integration for roster/leave; implement auto-exclusion engine; validate with Expertise data. | Wk 11–14
69 | Section 3.5.3 / SI-03 | Integration | Vehicle & equipment master sync (SAP PM / EAM) | Not Available | Equipment master integration framework supports SAP PM/EAM connectivity. Status synchronization (Active, Under Maintenance, Breakdown) requires bi-directional API configuration. | SAP Integration Architecture | SAP PM/EAM bi-directional sync requires API design, SAP CPI adapter configuration, and testing. | Design SAP PM integration specs; configure SAP CPI; test equipment master and status sync. | Wk 12–15
70 | Section 3.5.4 / SI-04 | Integration | Vendor & vendor-vehicle integration (SAP MM + PM) | Not Available | Vendor and vehicle-to-vendor association integration requires SAP MM + PM integration via SAP CPI for clear fleet segregation. | SAP Integration Architecture | SAP MM + PM integration for vendor-vehicle association requires SAP CPI configuration and testing. | Design SAP MM+PM integration; configure SAP CPI; test vendor master and equipment association sync. | Wk 12–15
71 | Section 3.5.5 / SI-05 | Integration | Maintenance & availability integration — block vehicle on maintenance (SAP PM) | Not Available | Maintenance blocking logic available in platform. SAP PM maintenance notification trigger and status synchronization requires integration development. | SAP Integration Architecture | SAP PM maintenance notification trigger and vehicle blocking logic requires integration development. | Develop SAP PM integration for maintenance notifications; implement vehicle blocking on maintenance status. | Wk 13–16
72 | Section 3.5.6 / SI-06 | Integration | Project, cost centre & financial integration (SAP PS / CO) | Not Available | Financial integration framework available. SAP PS/CO integration for WBS assignment, cost center allocation, and chargeback automation requires SAP CPI configuration. | SAP Integration Architecture | SAP PS/CO integration for project costing and chargeback requires SAP CPI configuration and testing. | Design SAP PS/CO integration; configure SAP CPI; test cost center and WBS posting with Expertise system. | Wk 13–17
73 | Section 3.5.7 / SI-07 | Integration | Automated cross-charge & vendor invoicing via SAP | Not Available | Cross-charge automation framework available. SAP MM/FI integration for automated vendor invoicing requires SAP CPI configuration and end-to-end testing. | SAP Integration Architecture | Automated vendor invoicing via SAP MM/FI requires integration design, SAP CPI configuration, and testing. | Design SAP MM/FI integration for vendor invoicing; configure SAP CPI; test end-to-end invoicing process. | Wk 14–17
74 | Section 3.5.7 / SI-08 | Integration | Alerts, events & notification integration (Fiori Inbox / email / SMS) | Not Available | In-app and email notifications available. SAP Fiori Inbox integration and SMS gateway configuration require additional setup. | Notification Module Config | SAP Fiori Inbox integration requires SAP CPI configuration. SMS gateway requires third-party SMS provider setup. | Configure SAP Fiori Inbox integration; set up SMS gateway; test multi-channel notification delivery. | Wk 14–16
75 | Section 3.5.8.2 / SI-09 | Integration | GPS (Saudi Ex) real-time integration | Not Available | GPS integration framework available with standard REST/API connectors. Saudi Ex GPS integration requires API specification from Saudi Ex and integration development. | GPS Integration Architecture | Saudi Ex GPS API specification required; real-time vehicle location, speed, idle time, and route adherence integration to be developed. | Obtain Saudi Ex API documentation; develop GPS integration; configure real-time data feed; test with live vehicles. | Wk 13–16
76 | Section 3.4.4 / SI-10 | Integration | ZKT Biotime attendance device integration | Not Available | Attendance data integration framework available. ZKT Biotime API/connector requires development for real-time attendance data sync to support driver availability tracking. | Integration Architecture | ZKT Biotime API integration for attendance data sync requires development. | Obtain ZKT Biotime API specs; develop integration connector; test attendance data sync. | Wk 13–15
77 | Section 3.4.1 / SI-11 | Integration | Petro APP fuel usage integration | Not Available | Fuel data integration framework available. Petro APP API integration requires specification from Expertise and connector development for fuel usage data sync per vehicle. | Integration Architecture | Petro APP API specification required for fuel usage data integration development. | Obtain Petro APP API documentation; develop integration; test fuel data sync per vehicle. | Wk 14–16
78 | Section 3.5.8.4 / SI-12 | Integration | KSA TGA / Naql / MIZAN regulatory data alignment | Not Available | Compliance data framework available. KSA regulatory authority integration (TGA, Naql, MIZAN) requires development of permit tracking, route validation, and regulatory alert workflows. | Compliance Module; Regulatory Integration Spec | KSA regulatory authority API access and integration for TGA, Naql, and MIZAN data alignment requires development. | Assess API availability from TGA/Naql/MIZAN; develop integration or structured data alignment workflows; implement permit and route validation. | Wk 14–17
79 | Section 3.10 / SI-13 | Integration | API integration layer (SAP CPI / PI-PO) config & error monitoring | Not Available | API-based integration architecture designed for SAP CPI/PI-PO compatibility. Error handling, monitoring, and retry logic framework available. Detailed configuration requires SAP environment access. | Technical Architecture Document | SAP CPI/PI-PO specific configuration requires access to Expertise SAP middleware environment for adapter setup and error monitoring. | Design integration architecture; configure SAP CPI adapters; implement error monitoring and alerting; conduct end-to-end testing. | Wk 12–16
GEO-FENCING & GPS TRACKING
80 | Section 3.5.8.1 / GF-01 | Build | Geo-fence definition for all vehicle categories (sites, depots, restricted zones) | Not Available | Geo-fence definition module supports polygon/radius-based geo-fences for project sites, offices, depots, pickup/drop locations, and restricted/high-risk zones across all vehicle categories. | Geo-fence Config Module – Application Demo | Integrate with GPS | Need to Integrate | Wk 10–13
81 | Section 3.5.8.1 / GF-02 | Build | Auto-trigger alerts (entry, exit, unauthorised deviation, time-based validation) | Not Available | Alert configuration supports auto-triggers on geo-fence entry, exit, unauthorized deviation, and time-based validation (early/delayed arrival) with multi-channel notification. | Geo-fence Alert Config – Demo | Integrate with SaudiEx | Need to Integrate | Wk 11–13
82 | Section 3.5.8.2 / GF-03 | Integration | GPS real-time tracking — live map view for transport admin | Not Available | Live map view framework available within the platform. Real-time GPS data display requires Saudi Ex GPS integration. |  | Real-time GPS vehicle location on live map requires Saudi Ex integration. | Integrate Saudi Ex GPS; configure live map view for transport admin; test real-time vehicle position updates. | Wk 13–16
83 | Section 3.5.8.2 / GF-04 | Build | Employee / passenger view — assigned vehicle, driver location & ETA | Not Available | Employee/passenger mobile view displays assigned vehicle details, driver location, and estimated arrival time for pickup/drop, reducing coordination calls. |  | Need to Develop | once GOS integration is done, this will be develped | Wk 14–16
84 | Section 3.5.8.3 / GF-05 | Build | Trip history logs (route, stops, deviations, duration) & audit replay | ⚠ Partially Available | Trip logging framework available. Full historical audit replay of GPS-tracked route, stops, deviations, and duration requires GPS integration data storage and replay feature development. | Trip Logging Module | GPS-based trip history replay requires Saudi Ex integration data retention and replay feature development. | Develop trip history storage from GPS feed; build audit replay feature with route visualization. | Wk 14–16
REPORTING, DASHBOARDS & ANALYTICS
85 | Section 3.7.1-A / RA-01 | Build | Management dashboard (fleet utilisation, costs, compliance, exceptions) | ✅ Fully Available | Management dashboard provides fleet utilization overview by category, cost per vehicle/route/project, compliance status summary, vendor vs owned performance, and exception alerts. | Management Dashboard – Application Demo | – | – | Wk 14–17
86 | Section 3.7.1-B / RA-02 | Build | Transport admin / operations dashboard (live GPS, availability, geo-fence alerts) | ⚠ Partially Available | Operations dashboard with availability, maintenance status, pending requests, and geo-fence violations available. Live GPS tracking requires Saudi Ex integration. | Operations Dashboard – Demo | Live GPS vehicle tracking on operations dashboard requires Saudi Ex GPS integration. | Integrate Saudi Ex GPS; configure live tracking on operations dashboard. | Wk 14–17
87 | Section 3.7.1-C / RA-03 | Build | HR / department dashboard (occupancy trends, allocation, eligibility compliance) | ✅ Fully Available | HR/Department dashboard displays employee transport utilization, seat occupancy trends, light vehicle allocation by department, and eligibility/policy compliance. | HR Dashboard – Application Demo | – | – | Wk 15–17
88 | Section 3.7.1-D / RA-04 | Build | Employee / passenger view dashboard (vehicle, driver, ETA) | ✅ Fully Available | Employee dashboard shows assigned vehicle and driver details, live pickup/drop tracking, and ETA visibility via mobile-friendly interface. | Employee Dashboard – Mobile Demo | – | – | Wk 15–17
89 | Section 3.7.2 / RA-05 | Build | Vehicle, driver, route & vendor KPI configuration | ✅ Fully Available | KPI configuration module covers all vehicle performance KPIs (utilization %, idle time, cost per km, maintenance cost, on-time %), driver KPIs (completion rate, violations), route efficiency KPIs, and vendor performance KPIs. | KPI Configuration Module – Demo | – | – | Wk 14–17
90 | Section 3.7.3 / RA-06 | Build | Vehicle capacity planner & utilisation optimiser | ✅ Fully Available | Capacity planning module covers seat capacity for buses, load capacity for heavy vehicles, forecasted vs actual utilization, and automatic recommendations for vehicle type, route consolidation, and trip merging. | Capacity Planner Module – Demo | – | – | Wk 15–18
91 | Section 3.7.4 / RA-07 | Build | Predictive & trend analytics (maintenance costs, demand forecasting) | ✅ Fully Available | Predictive analytics covers maintenance cost trend analysis, vehicle replacement recommendations, demand forecasting based on historical usage and project timelines, and seasonal demand analysis. | Analytics Module – Demo | – | – | Wk 16–19
92 | Section 3.7.5 / RA-08 | Integration | SAP-aligned financial & operational reports (cost centre, project/WBS, vendor) | Not Available | Operational reports available within the platform. SAP-aligned financial reports (cost center, WBS, vendor reconciliation) require SAP integration data feeds. | Reports Module; SAP Integration Spec | SAP financial data alignment for cost center/WBS reports requires SAP integration to be completed first. | Deliver SAP-aligned financial reports post SAP integration completion; configure report templates per Expertise chart of accounts. | Wk 16–19
93 | Section 3.7.2 / RA-09 | Build | Power BI export / read-only KPI exposure | ⚠ Partially Available | Excel/PDF export available. Power BI read-only KPI exposure via REST API or OData feed requires configuration of BI connector. | Reports Module | Power BI integration requires OData/REST API connector configuration for read-only KPI exposure. | Configure BI connector (OData/REST); validate Power BI connectivity with sample KPI dataset. | Wk 17–19
94 | Section 3.7.6 / RA-10 | Build | Report scheduling, drill-down & audit-ready reporting logs | ✅ Fully Available | Reporting module supports scheduled report distribution, drill-down from dashboard to transaction, multi-period comparison, export to Excel/PDF, and audit-ready reporting logs. | Reporting Module – Demo | – | – | Wk 16–19
95 | Section 3.7.3 / RA-11 | Build | What-if simulation — demand scenarios (peak/off-peak, fleet optimization) | ✅ Fully Available | What-if simulation module supports peak vs off-peak demand scenarios, fleet size optimization, and underutilized vehicle/overloaded assignment alerts. | Simulation Module – Demo | – | – | Wk 16–19
WORKFLOW BUILDER & APPROVAL FRAMEWORK
96 | Section 3.9.1 / WF-01 | Build | No-code / low-code workflow designer setup & configuration | ⚠ Partially Available | Visual workflow builder with configurable approval steps, conditions, and SLA rules available. Drag-and-drop no-code designer interface requires development/enhancement for full no-code capability. | Workflow Builder Module – Demo | Full drag-and-drop no-code workflow designer interface requires development/enhancement. | Develop enhanced no-code workflow designer UI; validate with Expertise workflow requirements. | Wk 8–10
97 | Section 3.9.2-A / WF-02 | Build | Transport request & allocation approval workflows (bus, light, heavy) | ✅ Fully Available | Approval workflows configured for all transport request types (bus allocation, light vehicle request, heavy vehicle movement) with role-based routing, parallel/sequential steps, and SLA escalation. | Workflow Builder – Transport Approval Config Demo | – | – | Wk 9–12
98 | Section 3.9.2-B / WF-03 | Build | Vehicle & asset lifecycle workflows (onboarding, decommission, ownership change) | ✅ Fully Available | Asset lifecycle workflows cover vehicle onboarding, decommissioning, ownership change (owned ↔ vendor), and temporary reassignment with full approval and audit trail. | Asset Lifecycle Workflow Config – Demo | – | – | Wk 9–12
99 | Section 3.9.2-C / WF-04 | Build | Employee & driver-related workflows (assignment, eligibility, licence expiry) | ✅ Fully Available | Driver assignment, eligibility validation, and license expiry exception handling workflows configured with approval routing and automated alert triggers. | Driver Workflow Config – Demo | – | – | Wk 10–12
100 | Section 3.9.2-D / WF-05 | Build | Vendor & RFQ approval workflows (RFQ, vendor selection, rate card) | ✅ Fully Available | Vendor and RFQ workflows cover RFQ approval, vendor selection, rate card approval, and exception cost approval with multi-level routing. | Vendor/RFQ Workflow Config – Demo | – | – | Wk 10–12
101 | Section 3.9.2-E / WF-06 | Build | Policy & exception handling workflows (geo-fence, out-of-policy, grade overrides) | ⚠ Partially Available | Grade override and out-of-policy workflows available. Geo-fence violation review and route deviation approval workflows require development. | Exception Workflow Config | Geo-fence violation review workflow and route deviation approval workflow require development. | Develop geo-fence violation review and route deviation approval workflows; configure escalation rules. | Wk 11–13
102 | Section 3.9.3 / WF-07 | Integration | SAP org structure & cost centre approval routing | Not Available | Cost center routing available within platform. SAP organizational structure-derived approver routing requires SAP org structure integration. | Workflow Config; SAP Integration Spec | SAP org structure-derived approver routing requires SAP HCM integration for org hierarchy data. | Integrate SAP org structure; configure workflow routing rules based on SAP cost center hierarchy. | Wk 13–15
103 | Section 3.9.4 / WF-08 | Build | Multi-channel notification config (in-app, email, SMS) | ✅ Fully Available | Multi-channel notifications configured for in-app, email, and SMS (configurable). Approval actions include Approve, Reject, Request Clarification with delegation and substitution. | Notification Config Module – Demo | – | – | Wk 12–14
104 | Section 3.9.5 / WF-09 | Build | Workflow audit trail, SLA breach tracking & version control | ✅ Fully Available | Complete audit trail of workflow configuration changes and approval decisions. Time-stamped approvals, SLA breach tracking, compliance reporting, and workflow version control. | Workflow Audit Module – Demo | – | – | Wk 13–15
TECHNICAL & NON-FUNCTIONAL
105 | Section 3.10 / TN-01 | Build | Cloud architecture setup, HA & DR configuration | ✅ Fully Available | Solution deployed on cloud-ready architecture with high availability (99.9% uptime SLA), disaster recovery configuration, and environment segregation (DEV/UAT/PROD). | Technical Architecture Document | – | – | Wk 4–7
106 | Section 3.11.4 / TN-02 | Build | DEV / UAT / PROD environment segregation | ✅ Fully Available | Three separate environments (DEV, UAT, PROD) maintained throughout the project with controlled promotion process and environment-specific access controls. | Environment Setup Guide | – | – | Wk 4–6
107 | Section 3.11.5 / TN-03 | Build | Role-based access control (RBAC) implementation | ✅ Fully Available | RBAC implemented across all modules with role definitions for Transport Admin, Fleet Manager, Driver, Employee, HR, Finance, and Executive roles. Workflow visibility controlled by role. | RBAC Config Module – Application Demo | – | – | Wk 8–10
108 | Section 3.11.5 / TN-04 | Build | Security — data encryption, RBAC, vulnerability assessment | ✅ Fully Available | Data encryption in transit (TLS 1.2+) and at rest. RBAC enforced across all modules. Regular vulnerability assessments and penetration testing conducted per industry standards. | Security Architecture Document | – | – | Wk 8–12
109 | Section 3.11.2 / TN-05 | UAT | UAT scripts preparation & execution | ✅ Fully Available | UAT scripts covering all functional scenarios prepared in Design phase and executed during UAT with defect tracking, resolution, and sign-off process. | UAT Script Template; Test Management Tool | – | – | Wk 20–23
110 | Section 3.11.4 / TN-06 | UAT | Performance & scalability testing | ✅ Fully Available | Performance testing conducted to validate response times, concurrent user load, and scalability requirements. Bottlenecks identified and resolved before go-live. | Performance Test Plan | – | – | Wk 20–22
111 | Section 3.6.1 / TN-07 | UAT | Mobile-friendly UI validation | ✅ Fully Available | Application UI validated for mobile responsiveness across iOS and Android devices. Driver and employee-facing views optimized for mobile usage. | Mobile UI Test Plan; Device Test Results | – | – | Wk 20–22
112 | Section 3.11.1 / TN-08 | UAT | Issue resolution log & root cause analysis (UAT) | ✅ Fully Available | Issue resolution log maintained throughout UAT with defect classification, root cause analysis, fix validation, and closure documentation. | Issue Log / Defect Tracking Tool | – | – | Wk 21–24
DOCUMENTATION
113 | Section 3.11.2 / DO-01 | Design | Business blueprint (AS-IS & TO-BE processes) | ✅ Fully Available | Business blueprint document covers all AS-IS process documentation and TO-BE process design across all T&L modules agreed with Expertise stakeholders. | Business Blueprint Document Template | – | – | Wk 4–7
114 | Section 3.11.2 / DO-02 | Build | Configuration manuals & WRICEF functional/technical specifications | ✅ Fully Available | Configuration manuals and WRICEF (Workflow, Reports, Interfaces, Conversions, Enhancements, Forms) functional/technical specifications prepared for all custom objects. | Configuration Manual Template | – | – | Wk 14–18
115 | Section 3.11.2 / DO-03 | Integration | Integration documentation (SAP, GPS, ZKT, Petro APP) | ✅ Fully Available | Integration documentation covers all interface specifications, API mapping, data flow diagrams, error handling, and monitoring for SAP, GPS, ZKT, and Petro APP integrations. | Integration Specification Template | – | – | Wk 15–18
116 | Section 3.11.3 / DO-04 | UAT | User manuals & role-specific guides | ✅ Fully Available | User manuals and role-specific quick reference guides prepared for all user roles: Transport Admin, Fleet Manager, Driver, Employee, HR, Finance, and Management. | User Manual Template | – | – | Wk 20–22
117 | Section 3.11.3 / DO-05 | UAT | Video tutorials & quick reference guides | ✅ Fully Available | Video tutorials and quick reference guides prepared for key user scenarios covering request submission, approval, allocation, compliance, and reporting. | Training Material Templates | – | – | Wk 21–23
118 | Section 3.11.2 / DO-06 | UAT | AMS operational documents (escalation matrix, issue resolution workflows) | ✅ Fully Available | AMS operational documentation covers support escalation matrix, issue resolution workflows, SLA definitions, and incident management process. | AMS Operational Document Template | – | – | Wk 22–24
119 | Section 3.11.2 / DO-07 | Go-Live | Go-live & post-go-live cutover / stabilisation plan | ✅ Fully Available | Go-live cutover plan covers pre-go-live checklist, cutover sequence, go/no-go criteria, rollback plan, and post-go-live stabilization activities and support structure. | Go-Live Plan Template | – | – | Wk 24–25
120 | Section 3.11.2 / DO-08 | UAT | Change management documentation | ✅ Fully Available | Change management documentation covers stakeholder impact assessment, communication plan, training needs analysis, adoption metrics, and change champion identification. | Change Management Document Template | – | – | Wk 22–24
121 | Section 2.4 / DO-09 | Inception | Weekly status report template & progress tracking process | ✅ Fully Available | Weekly status report template covers milestone progress, risk register update, issue log, action items, and next week plan. Distributed to all stakeholders. | Status Report Template | – | – | Inception – Continuous
TRAINING, GO-LIVE & POST GO-LIVE
122 | Section 3.11.3 / TG-01 | UAT | Train-the-trainer sessions | ✅ Fully Available | Train-the-trainer program equips key Expertise users to independently train end users. Covers all modules with hands-on practice sessions and Q&A. | Training Plan; TTT Session Materials | – | – | Wk 22–24
123 | Section 3.11.3 / TG-02 | UAT | End-user training — functional & technical | ✅ Fully Available | Role-based end-user training sessions covering all functional and technical aspects for each user group with hands-on system walkthroughs. | Training Plan; Training Materials | – | – | Wk 23–25
124 | Section 3.11.3 / TG-03 | Go-Live | Post-go-live workshops & adoption review | ✅ Fully Available | Post-go-live workshops conducted to address user challenges, review adoption metrics, and identify optimization opportunities. Lessons learned documented. | Post-Go-Live Workshop Plan | – | – | Wk 28–30
125 | Section 3.11.2 / TG-04 | Go-Live | Cut-over / go-live execution & hypercare | ✅ Fully Available | Go-live execution managed per cutover plan with dedicated hypercare team providing on-site and remote support during the critical stabilization period. | Cutover Plan; Hypercare Support Plan | – | – | Wk 26
126 | Section 2.4 / TG-05 | Go-Live | Post go-live stabilisation support (2 months) | ✅ Fully Available | 2-month post-go-live stabilization support provided with dedicated support team, issue tracking, priority resolution, and weekly review meetings. | Post-Go-Live Support SLA | – | – | Wk 27–34
127 | Section 2.4 / TG-06 | Go-Live | Lessons learned & final project closure report | ✅ Fully Available | Lessons learned workshop conducted and final project closure report prepared covering achievements vs plan, key learnings, recommendations, and formal project sign-off. | Project Closure Report Template | – | – | Wk 33–34
128 | Section 3.11.2 / TG-07 | Support | AMS SLA performance report & issue resolution log | ✅ Fully Available | Monthly AMS SLA performance reports cover ticket volume, resolution times, SLA compliance, root cause analysis, and system optimization records. | AMS SLA Reporting Template | – | – | Support – Continuous